## Product Backlog
| PRODUCT BACKLOG | Notes: There are three types of user accounts: Admin, publisher/shop owner and public user.
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | As a shop owner, I want to remove a book entry, so that I can have number of books under the limit. |  | High | 3 | Done | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
2 | As a Shop owner, I want to edit book’s author information , so that the book’s author information is correct. |  | High | 3 | In progress | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
3 | As a Shop owner, I want to change the selling price of a book, so that I can sell the book to the customer at a new price. |  | High | 3 | To Do | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
4 | As a shop owner, I want to change the status of a book to available, so that I can Sell the book to the customer. |  | High | 3 | To Do | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
5 | As a shop owner, I want to change the status of a book, so that I can make the book unavailable to the customer. |  | High | 3 | To Do | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
6 | As an Admin, I want to search for transactions by month so that I can see how many books were sold on the platform each month. |  | Medium | 5 | To Do | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
7 | As an Admin, I want be able to approve or block new users so that I can allow only legal users to be members. |  | Critical | 5 | Done | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
8 | As an Admin I want be able to edit the details of books so that I can keep all the books up to date |  | Critical | 3 | To Do | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
9 | As an Admin I want to be able to remove books that violate the rules so that the book can no longer be displayed. |  | High | 3 | To Do | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
10 | As an Admin I want to be able to edit the details of a user so that the user’s profile doesn’t show any incorrect details |  | High | 3 | Done | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
11 | As an Admin I want To be able to add a new user so that Person can start buying or selling books. |  | Medium | 3 | To Do | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
12 | As an Admin I want to be able to download report of a book So that I can inspect certain stats about that book |  | Medium | 5 | To Do | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
13 | As an Admin I want to be able to terminate accounts so that I can remove offending accounts. (after account registration) |  | Medium | 5 | To Do | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
15 | As a public user I want to browse books based on author, ISBN or book title by entering into the search field so that I can quickly find the book based on different search criteria. |  | Critical | 5 | Done | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
16 | As a public user I want to browse books based on categories by selecting a dropdown menu so that I can quickly find the book of my favourite categories. |  | Critical | 5 | Done | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
17 | As a public user I want to add a book to my cart so that I can keep track of the book I want to buy. |  | Critical | 8 | Done | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
18 | As a public user I want to publish my used book to the website so that I can advertise my books to other users |  | Critical | 3 | Done | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
19 | As a public user I want to add a review to a user so that I can let other people know about the service the user provides. |  | Medium | 8 | To Do | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
20 | As a public user I want to edit book details so that I can display the most up-to-date information I want for the book. |  | High | 3 | Done | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
21 | As a public user I want to receive notification when someone makes a purchase of my published books so that I can take actions such as delivering the books to the buyer. |  | Critical | 8 | To Do | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
22 | As a public user I want to add a book to my cart and buy books so that I don't have to go to the bookstore to buy books. |  | Critical | 8 | Done | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
23 | As a public user, I want to register my account so that I can start using the system. |  | Critical | 5 | Done | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
24 | As an admin/shop owner/public user, I want to see my profile information so that I can confirm that all of my information is correct. |  | Critical | 5 | Done | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
25 | As a public user, I want to login my account so that I can start using the system. |  | Critical | 5 | Done | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
26 | As a public user, I want to see the contact us page so that I can know how to contact and give feedback |  | Low | 3 | Done | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.
27 | As a public user, I want to see the about us page so that I can know more information about the platform |  | Low | 3 | Done | Unit tests have been written and passed. Code is well formatted and suitable code comments are provided. Acceptance criteria for the User Stories is met. Signed off by Product Owner. Code review is completed.

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As a shop owner, I want to remove a book entry, so that I can have number of books under the limit. | #N/A | #N/A | #N/A | #N/A | #N/A
2 | As a Shop owner, I want to edit book’s author information , so that the book’s author information is correct. | #N/A | #N/A | #N/A | #N/A | #N/A
3 | As a Shop owner, I want to change the selling price of a book, so that I can sell the book to the customer at a new price. | #N/A | #N/A | #N/A | #N/A | #N/A
4 | As a shop owner, I want to change the status of a book to available, so that I can Sell the book to the customer. | #N/A | #N/A | #N/A | #N/A | #N/A
5 | As a shop owner, I want to change the status of a book, so that I can make the book unavailable to the customer. | #N/A | #N/A | #N/A | #N/A | #N/A
6 | As an Admin, I want to search for transactions by month so that I can see how many books were sold on the platform each month. | #N/A | #N/A | #N/A | #N/A | #N/A
7 | As an Admin, I want be able to approve or block new users so that I can allow only legal users to be members. | #N/A | #N/A | #N/A | #N/A | #N/A
8 | As an Admin I want be able to edit the details of books so that I can keep all the books up to date | #N/A | #N/A | #N/A | #N/A | #N/A
9 | As an Admin I want to be able to remove books that violate the rules so that the book can no longer be displayed. | #N/A | #N/A | #N/A | #N/A | #N/A
10 | As an Admin I want to be able to edit the details of a user so that the user’s profile doesn’t show any incorrect details | #N/A | #N/A | #N/A | #N/A | #N/A
11 | As an Admin I want To be able to add a new user so that Person can start buying or selling books. | #N/A | #N/A | #N/A | #N/A | #N/A
12 | As an Admin I want to be able to download report of a book So that I can inspect certain stats about that book | #N/A | #N/A | #N/A | #N/A | #N/A
13 | As an Admin I want to be able to terminate accounts so that I can remove offending accounts. (after account registration) | #N/A | #N/A | #N/A | #N/A | #N/A
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | As a public user I want to browse books based on author, ISBN or book title by entering into the search field so that I can quickly find the book based on different search criteria. | #N/A | #N/A | #N/A | #N/A | #N/A
17 | As a public user I want to browse books based on categories by selecting a dropdown menu so that I can quickly find the book of my favourite categories. | #N/A | #N/A | #N/A | #N/A | #N/A
18 | As a public user I want to add a book to my cart so that I can keep track of the book I want to buy. | #N/A | #N/A | #N/A | #N/A | #N/A
19 | As a public user I want to publish my used book to the website so that I can advertise my books to other users | #N/A | #N/A | #N/A | #N/A | #N/A
20 | As a public user I want to add a review to a user so that I can let other people know about the service the user provides. | #N/A | #N/A | #N/A | #N/A | #N/A
21 | As a public user I want to edit book details so that I can display the most up-to-date information I want for the book. | #N/A | #N/A | #N/A | #N/A | #N/A
22 | As a public user I want to receive notification when someone makes a purchase of my published books so that I can take actions such as delivering the books to the buyer. | #N/A | #N/A | #N/A | #N/A | #N/A
23 | As a public user I want to add a book to my cart and buy books so that I don't have to go to the bookstore to buy books. | #N/A | #N/A | #N/A | #N/A | #N/A
24 | As a public user, I want to register my account so that I can start using the system. | #N/A | #N/A | #N/A | #N/A | #N/A
25 | As an admin/shop owner/public user, I want to see my profile information so that I can confirm that all of my information is correct. | #N/A | #N/A | #N/A | #N/A | #N/A